## Test Plan
Test Plan for Aarong

## Test Scenarios
Project Name | Aarong
Reference Document
Created By | Jasmin Akter Purnima
Creation Date | 2024-10-26
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TC_001 |  | Validate the URL in different browsers. | P0 | 1
TC_002 |  | Validate the "Login" functionality. | P1 | 25
TC_003 |  | Validate the "Sign Up" functionality. | P1 | 48
TC_004 |  | Validate the "Forgot your password?" functionality. | P4 | 5
TC_005 |  | Validate data transfer security during login and sign up. | P2 | 8
TC_006 |  | Validate the Main Navigation Menu functionality. | P3 | 10
TC_007 |  | Validate the image and visual elements on the homepage. | P3 | 5
TC_008 |  | Validate the "Logout" functionality. | P2 | 8

## TestCase
Test Case for Aarong Application | [12 empty] | Test Case
Project Name | Aarong | TC Developed By | Jasmin Akter Purnima | [9 empty] | Pass | 94
Module Name | Sign Up & Login | TC Reviewed By | Ehsanul Alam Sabbir | [9 empty] | Fail | 10
Developer Name |  | TC Execution Start Date | [10 empty] | No Run | 0
TC Start Date | 2024-11-10 | TC Execution End Date | [10 empty] | Blocked | 0
TC End Date | 2024-11-15 | Browser(Tested) | Yes | [9 empty] | Total | 104
Performance(Tested)
Test Executed By
SL No | Module | Type of testing | Features | Test Cases | Expected Result | Actual Result | Reproducing Steps | Reproducing Steps | Bugs Screenshot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checking by running the URL site in different browsers. | Should be run in different browsers | Found as per expectation | Browsers-Chrome, Firefox, Opera | 1. Go to different browsers. 2. Search 'Aarong' 3. Go to the website |  |  | Passed
2 | User Management | UI Testing | Sign Up | Checking the "Sign Up" form is visible and easily accessible on the main page. | Should be clearly visible, prominent | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this. |  |  | Passed
3 |  |  |  | Checking spelling or grammatical mistakes. | No spelling or grammatical mistakes. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this. |  |  | Passed
4 |  |  |  | Verifying the font, text color & style. | Should be as per the requirements. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this. |  |  | Passed
5 |  |  |  | Verifying that all fields in the form are aligned uniformly. | Should be left or centered with consistent spacing between them. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this field. |  |  | Passed
6 |  |  |  | Verifying that all buttons in the form are aligned uniformly. | Proper alignment should be present. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check all buttons. |  |  | Passed
7 |  |  |  | Verifying the mandatory field is marked with an asterisk. | Should be clearly marked with asterisk. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check * this. |  |  | Passed
8 |  |  |  | Verifying the " Continue" button hovering or not. | When hovering the button should be changed the color. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check hovering this field. |  |  | Passed
9 |  |  |  | Checking hover by clicking over the fields. | Fields color should be changed. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check hovering all fields. |  |  | Passed
10 |  |  |  | Checking that there’s an eye icon to toggle password visibility. | The password visibility toggle icon should be present, clearly visible. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check eye icon field. |  |  | Passed
11 |  |  |  | Verifying each field is highlighted(color change) when clicked or in focus. | Should have a clear, visual indicator (color change) when in focus. | Not found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check all fields. | No color change error |  | Failed
12 |  |  |  | Checking checkbox "I agree to Aarong's Term & Conditions." | Checkbox should be present. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check the checkbox feild. |  |  | Passed
13 |  | Functional Testing |  | Verifying the "First Name" field is present on the form. | Should be visible and clickable. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check first name feild. |  |  | Passed
14 |  |  |  | Verifying the "Last Name" field is present on the form. | Should be visible and clickable. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check last name feild. |  |  | Passed
15 |  |  |  | Verifying the "Mobile Number" field is present on the form. | Should be visible and clickable. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check mobile number feild. |  |  | Passed
16 |  |  |  | Checking the "Gender" dropdown is present on the form. | Dropdown should be visible and clickable. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check gender feild. |  |  | Passed
17 |  |  |  | Checking that the "First Name" field is mandatory and does not allow form submission if it's empty. | An error message should display if the field is empty. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this empty feild. |  |  | Passed
18 |  |  |  | Checking that the "Last Name" field is mandatory and does not allow form submission if it's empty. | An error message should display if the field is empty. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this empty feild. |  |  | Passed
19 |  |  |  | Checking that the "Mobile Number" field is mandatory and does not allow form submission if it's empty. | An error message should display if the field is empty. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this empty feild. |  |  | Passed
20 |  |  |  | Checking by clicking on the submit button for blank input. | Should not allow user to sign up and pop an error message. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check submit button for empty field. |  |  | Passed
21 |  |  |  | Checking firstname and lastname field is case insensitive | Should accept the provided input. | Found as per expectation | aaAaBac yYzzA | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
22 |  |  |  | Checking firstname and lastname with numbers. | Should not accept a number as provided input. | Not found as per expectation | 12345 67890 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. | Number errors in first and last name |  | Failed
23 |  |  |  | Checking first name and last name with special characters. | Should not accept this special character as provided input. | Not found as per expectation | @#$% &*!~ | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. | Special character error |  | Failed
24 |  |  |  | Checking firstname and lastname with decimal numbers. | Should not accept these decimal numbers as provided input. | Not found as per expectation | .arASp .GSdfh | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. | Decimal number error |  | Failed
25 |  |  |  | Checking firstname and lastname with alphanumeric characters. | Should accept the provided input. | Found as per expectation | Priya44 Jahan66 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
26 |  |  |  | Checking firstname and lastname with alphabets. | Should accept the provided input. | Found as per expectation | Priya Jahan | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
27 |  |  |  | Checking comma between alphabets for firstname and lastname. | Should reject this value as provided input. | Not found as per expectation | Pri,ya Jah,an | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. | Comma error |  | Failed
28 |  |  |  | Checking that the firstname and lastname field has a maximum character limit. | An error should display if fewer than the maximum characters are entered. | Not found as per expectation | Lorem Ipsum is simply dummy text of the printing and typesetting industry. Lorem Ipsum has been the industry's standard dummy text ever since the 1500s, when an unknown printer took a galley of type and scrambled it to make a type specimen book. It has survived not only five centuries, but also the leap into electronic typesetting, remaining essentially unchanged. It was popularised in the 1960s with the release of Letraset sheets containing Lorem Ipsum passages, and more recently with desktop publishing software like Aldus PageMaker including versions of Lorem Ipsum. | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this feild. | Maximum character limit error |  | Failed
29 |  |  |  | Checking that the firstname and lastname field has a minimum character limit | An error should display if fewer than the minimum characters are entered. | Not found as per expectation | a b | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. | Minimum character limit error |  | Failed
30 |  |  |  | Checking newsletter checkbox. | Should function successfully. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this checkbox. |  |  | Passed
31 |  |  |  | Checking mobile number with numeric value. | Should accept the provided input. | Found as per expectation | 1700000000 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
32 |  |  |  | Checking mobile number with alphanumeric value. | The field should reject alphanumeric input. | Found as per expectation | 017ab000000 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
33 |  |  |  | Check if the form prevents submission if the mobile number is already registered. | An error message should appear for duplicate mobile numbers. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check already registered number. |  |  | Passed
34 |  |  |  | Checking that the mobile number field validates the correct phone number format. | An error should display if the entered number does not match the format. | Found as per expectation | 1630760000 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field.. |  |  | Passed
35 |  |  |  | Checking that the gender dropdown is mandatory and does not allow form submission if it's unselected. | An error message should display if the field is not selected. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this feild. |  |  | Passed
36 |  |  |  | Verifying that the form can be cleared if a "Reset" button is available. | Clicking "Reset" should clear all input fields. | Not found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this button. | Don't have reset button |  | Failed
37 |  |  |  | Verifying that the "Continue" button is only enabled when all mandatory fields are filled in correctly. | Should be inactive until all fields meet the validation requirements. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this button. |  |  | Passed
38 |  |  |  | Checking the "Email" field is present on the form. | Should be visible and clickable. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this feild. |  |  | Passed
39 |  |  |  | Checking the "Date of Birth" field is present on the form. | Should be visible and clickable. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this feild. |  |  | Passed
40 |  |  |  | Checking the "Create Password" field is present on the form. | Should be visible and clickable. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this feild. |  |  | Passed
41 |  |  |  | Checking the "Confirm Password" field is present on the form. | Should be visible and clickable. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this feild. |  |  | Passed
42 |  |  |  | Checking the "Email" field is mandatory and doesn't allow form submission if it's empty. | An error message should display if the field is empty. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this empty feild. |  |  | Passed
43 |  |  |  | Validating an email id can only be used one time. | Should not allow user to register and display an error message. | Found as per expectation | jazpriya88@gmail.com | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
44 |  |  |  | Checking by inputting invalid email format. | Should accept the provided input. | Found as per expectation | jazpriya88@@@gmail.com | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
45 |  |  |  | Checking by inputting valid email format. | Should not accept the provided input and display an error message. | Found as per expectation | jazpriya88@gmail.com | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
46 |  |  |  | Checking that the date picker works correctly when selecting a date in the date of birth field. | Should open and allow the user to select a valid date. | Found as per expectation | 11/25/1999 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
47 |  |  |  | Verifying the "Create Password" field is mandatory and doesn't allow form submission if it's empty. | An error message should display if the field is empty. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this feild. |  |  | Passed
48 |  |  |  | Validating that "Confirm Password" matches the "Create Password" field. | An error message should appear if the passwords do not match. | Found as per expectation | priya240 priyaaa24 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check * this feild. |  |  | Passed
49 |  |  |  | Checking. that the "Create Password" field enforces a minimum character limit. | Should display an error if the password does not meet the minimum length. | Found as per expectation | priya240 priya240 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
50 |  |  |  | Checking that the "Create Password" field enforces complexity. | Should display an error if the password does not meet requirements. | Found as per expectation | priya240 priya241 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
51 |  |  |  | Check that the passwords entered in password fields are hidden. | Both password fields should hide the entered characters. | Found as per expectation | priya240 priya242 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
52 |  |  |  | Verifying that the form is submitted successfully when all fields contain valid data. | User should receive a confirmation or be redirected to a success page. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this feild. |  |  | Passed
53 |  |  |  | Checking that clicking the back button the user to the previous step of the form. | Should be taken back to the first step of account creation. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this back button. |  |  | Passed
54 |  |  |  | Validating OTP is sent to the registered phone/email when the login button is clicked. | User should receive an OTP to the registered phone number or email. | Found as per expectation | 923009 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
55 |  |  |  | Checking that the user can login by entering a valid OTP. | User is successfully logged in. | Found as per expectation | 923009 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
56 |  |  |  | Checking by inputting an incorrect OTP. | An error message should display. | Found as per expectation | 923000 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
57 |  |  |  | Checking that the system does not allow login with an expired OTP. | Message "OTP expired" is displayed, and login failed. | Found as per expectation | 923009 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
58 |  |  |  | Checking that the user can request a new OTP if needed. | A new OTP is sent to the registered phone number or email. | Found as per expectation | 750008 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
59 |  |  |  | Checking that the OTP field does not accept non numeric characters. | Should not accept a non numeric characters as provided input. | Found as per expectation | ab99880 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. |  |  | Passed
60 |  |  |  | Checking that the user is directed to the appropriate landing page after a successful login. | User should be redirected to the appropriate landing page. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field. |  |  | Passed
61 |  | UI Testing | Login | Checking that the overall layout of the login page is clean and responsive. | All elements are properly aligned, and the page layout is responsive. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check all layout. |  |  | Passed
62 |  |  |  | Verify login page title. | The title should be as client requirement. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check title. |  |  | Passed
63 |  |  |  | Checking that the Aarong logo is visible. | The logo is displayed clearly at the top of the page. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check logo. |  |  | Passed
64 |  |  |  | Checking that the "Email" and "Password" input fields are properly aligned. | Both fields are aligned properly . | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check those fields allignment. |  |  | Passed
65 |  |  |  | Checking that the "Login" button is prominently displayed and aligned correctly. | The button is clearly visible, centered, or aligned as per design | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this button. |  |  | Passed
66 |  |  |  | Verifying that the "Forgot Password?" link is visible. | Should be visible and clickable. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this mentioned field. |  |  | Passed
67 |  |  |  | Checking that the font style and size are consistent. | Should be as per the requirements | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check all page font style. |  |  | Passed
68 |  |  |  | Verifying each field is highlighted(color change) when clicked or in focus. | Should have a clear, visual indicator (color change) when in focus. | Not found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check all this field. | No color change error |  | Failed
69 |  |  |  | Verifying the " Login" button hovering or not. | when hovering the button should be changed the color. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Lohin" button and put data on the mentioned field. |  |  | Passed
70 |  |  |  | Checking the placement of error messages when incorrect information is entered. | An error message is displayed near the input field. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this field hovering. |  |  | Passed
71 |  | Functional Testing | Login | Checking that the login page loads without any errors. | The page loads completely with all elements visible. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this page. |  |  | Passed
72 |  |  |  | Verifying the email or mobile number is accepts as input. | Field should accept alphanumeric input. | Found as per expectation | jazpriya88@gmail.com | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field. |  |  | Passed
73 |  |  |  | Verifying the "Continue" button when no email or mobile number is entered. | An error message should display if the field is empty. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this button. |  |  | Passed
74 |  |  |  | Checking that the user can log in with a valid email/mobile number. | User is successfully logged in. | Found as per expectation | jazpriya88@gmail.com | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field. |  |  | Passed
75 |  |  |  | Checking that the user can log in with an invalid email/mobile number. | User shouldn't successfully logged in. | Found as per expectation | jazpriya8847@@gmail.com | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field. |  |  | Passed
76 |  |  |  | Verify the displayed error message spell should be correct. | An error message should display. | Found as per expectation | jazzzpriyaa88@gmail.com | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field. |  |  | Passed
77 |  |  |  | Checking that the user can log in with a valid password. | User is successfully logged in. | Found as per expectation | 123456 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field. |  |  | Passed
78 |  |  |  | Checking that the user can log in with an invalid password. | An error message should display. | Found as per expectation | 125890077 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field. |  |  | Passed
79 |  |  |  | Verifying the "Continue" button after entering a valid email or mobile number. | System proceeds to the password entry step. | Found as per expectation | jazpriya88@gmail.com | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field. |  |  | Passed
80 |  |  |  | Verifying that the system identifies an invalid email format. | An error message should display. | Found as per expectation | jazpriya8847@@gmail.com | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field. |  |  | Passed
81 |  |  |  | Verifying that the password input field is masked. | Password is masked, showing dots instead of characters. | Found as per expectation | 123456 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field. |  |  | Passed
82 |  |  |  | Verify that the "Forgot Password?" link is functional. | The user should be redirected to the password recovery page. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this field. |  |  | Passed
83 |  |  |  | Checking a valid registered email address and click the "Submit" button for forgot password. | Message to reset the password should be sent to the provided email. | Found as per expectation | jazpriya88@gmail,com | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field and click submit button. |  |  | Passed
84 |  |  |  | Verify user should be login successfully with the new password not by the old password. | User is successfully logged in. | Found as per expectation | 5678900 | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field and click submit button. |  |  | Passed
85 |  |  |  | Checking that the Facebook login button redirects to the Facebook login page. | User should be redirected to the login page. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this button. |  |  | Passed
86 |  |  |  | Checking that the Google login button redirects to the Google login page. | User should be redirected to the login page. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this button. |  |  | Passed
87 |  |  |  | Checking that the "Sign Up Now" link redirects the user to the registration page. | User should be redirected to the registration page. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this link. |  |  | Passed
88 |  |  |  | Verify the login form and observe whether a CAPTCHA is present. | CAPTCHA should be displayed below the username and password fields. | Not found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this feild is present or not. | CAPTCHA should not display |  | Failed
89 |  |  |  | Checking the user is redirected to the correct page after a successful login. | User should be redirected to the designated dashboard. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this successfully. |  |  | Passed
90 |  |  |  | Checking that the navigation menu is displayed at the top of the homepage. | Navigation menu should be visible on the homepage. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check all main menu. |  |  | Passed
91 |  |  |  | Verifying that each main menu item is present and labeled correctly. | Should be present and accurately labeled. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check all main menu's label. |  |  | Passed
92 |  |  |  | Verifying that click on each main menu item. | Each menu item should be clickable. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check each menu item. |  |  | Passed
93 |  |  |  | Verifying that the hovering over each main menu item. | Should be hovering when each main menu item appears. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field. |  |  | Passed
94 |  |  |  | Checking that the submenu items are displayed correctly. | Should be hovering when each submenu item appears. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and put data on the mentioned field. |  |  | Passed
95 |  |  |  | Checking that each image on the homepage for clear, sharpness, and appropriate resolution. | All images are of high quality, clear. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check all images. |  |  | Passed
96 |  |  |  | Checking that click on each clickable image or promotional banner. | Each image should be redirected the user to the correct page. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check promotional banner. |  |  | Passed
97 |  |  |  | Verifying that the "Remove Account" link is clickable. | Should be visible and clickable. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this field. |  |  | Passed
98 |  | Functional Testing | Logout | Checking that the "Logout" option is displayed in the account menu. | Should be visible in the account menu after logging in. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button. 4. Click on "My account" sign and check "Logout" button. |  |  | Passed
99 |  |  |  | Checking that click on the "Logout" option. | User should be successfully logged out and redirected to the login page. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button. 4. Click on "My account" sign and click on "Logout" button. |  |  | Passed
100 |  |  |  | Verifying that attempt to access a page that requires authentication after logging out. | Access to the page is denied, and redirected to the login page. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button. 4. Click on "My account" sign and click on "Logout" button. |  |  | Passed
101 |  |  |  | Checking that click on "Logout" and observe if a logout confirmation message appears. | confirmation message is displayed. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button. 4. Click on "My account" sign and click on "Logout" button and observe the confirmation page. |  |  | Passed
102 |  |  |  | Checking that the page to observe if the message "You have signed out and will go to our homepage in 5 seconds" appears. | Message indicating automatic redirection in 5 seconds is visible. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button. 4. Click on "My account" sign and click on "Logout" button and observe the page to check the message. |  |  | Passed
103 |  |  |  | Verifying that the logout confirmation page for any personal information. | No sensitive information should be displayed on the page. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button. 4. Click on "My account" sign and click on "Logout" button. |  |  | Passed
104 |  |  |  | Checking that the logout page for any error messages or warnings. | No error messages are displayed on the logout confirmation page. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button. 4. Click on "My account" sign and click on "Logout" button. |  |  | Passed
105 |  |  |  | Checking that refresh the page and observe the countdown timer. | The page redirects to the homepage after 5 seconds. | Found as per expectation | N/A | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button. 4. Click on "My account" sign and click on "Logout" button. |  |  | Passed

## Test Summary
Test Case Report
Project Name | Aarong |  |  |  |  | Result:
Module Name | Account |  |  |  |  | Total No. | Status
Feature Name | Sing Up & Login |  |  |  |  | 94 | Pass
Test Case Version | 1 |  |  |  |  | 10 | Fail
Written By | Jasmin Akter Purnima |  |  |  |  | 0 | Not Executed | New Features | Testing Scope: | Testing Environment: Google Chrome Browser
Executed By | Jasmin Akter Purnima |  |  |  |  | 0 | Out of Scope
Reviewed By
Test Execution Report
Test Case | Pass | Fail | Not Executed | Out of Scope | Total Test Case
| 94 | 10 | 0 | 0 | 104
Grand Total | 94 | 10 | 0 | 0 | 104
Limitations
Documents |  | Reviewed | Useful
PRD |  | No | No
User Story |  | No | No
| Testing Type in Scope | Description
Yes/ No Justification (if No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No Justification (if No): | Intigration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No Justification (if No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No Justification (if No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No Justification (if No): | Browser Compatability Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No Justification (if No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No Justification (if No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Or Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting | Bug Reporting | Bug Reporting
# SL 11 | # SL 22 | # SL 23
Issue: Each field isn't highlighted(color change) when clicked or in focus. | Issue: First and last names should not start with number. | Issue: First and last names should not start with a special character.
Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check all fields. | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field.
Env: Production. | Env: Production. | Env: Production.
Module: "Sign UP" | Module: "Sign UP" | Module: "Sign UP"
Priority: P1 | Priority: P1 | Priority: P1
Severity: Minor | Severity: Major | Severity: Major
Screenshot: No color change | Screenshot: Number errors in first and last name | Screenshot: Special character error
Expected Result: Should have a clear, visual indicator (color change) when in focus. | Expected Result: Should not accept a number as provided input. | Expected Result: Should not accept this special character as provided input.
Responsible QA: Jasmin Akter Purnima | Responsible QA: Jasmin Akter Purnima | Responsible QA: Jasmin Akter Purnima
Bug Reporting | Bug Reporting | Bug Reporting
# SL 24 | # SL 27 | # SL 28
Issue: First and last names should not start with decimal number. | Issue: First and last names should not accept comma . | Issue: Firstname and lastname field should not accept maximum character limit.
Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field.
Env: Production. | Env: Production. | Env: Production.
Module: "Sign UP" | Module: "Sign UP" | Module: "Sign UP"
Priority: P1 | Priority: P1 | Priority: P1
Severity: Minor | Severity: Major | Severity: Major
Screenshot: Decimal number error | Screenshot: Comma error | Screenshot: Maximum character limit error
Expected: Should not accept these decimal numbers as provided input. | Expected Result: Should reject this value as provided input. | Expected: Should have a clear, visual indicator (color change) when in focus.
Responsible QA: Jasmin Akter Purnima | Responsible QA: Jasmin Akter Purnima | Responsible QA: Jasmin Akter Purnima
Bug Reporting | Bug Reporting | Bug Reporting
# SL 29 | # SL 36 | # SL 88
Issue: Firstname and lastname field should not accept minimum character limit. | Issue: The form can be cleared if a "Reset" button is available. | Issue: In he login form and observe whether a CAPTCHA is present.
Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and put data on the mentioned field. | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Sign Up Now" button and check this button is present or not. | 1. Go to the URL https://www.aarong.com/ 2. Click on the "My Account" button in the right corner. 3. Click the "Login" button and check this feild is present or not.
Env: Production. | Env: Production. | Env: Production.
Module: "Sign UP" | Module: "Sign UP" | Module: "Login"
Priority: P1 | Priority: P1 | Priority: P1
Severity: Minor | Severity: Minor | Severity: Major
Screenshot: Minimum character limit error | Screenxhot: Don't have any reset button | Screenshot: CHAPCHA shouldn't display
Expected Result: An error should display if fewer than the minimum characters are entered. | Expected Result: Clicking "Reset" should clear all input fields. | Expected Result: CAPTCHA should be displayed below the username and password fields.
Responsible QA: Jasmin Akter Purnima | Responsible QA: Jasmin Akter Purnima | Responsible QA: Jasmin Akter Purnima

## Test Metrics
Test Metrics
SL No | Metrics | Description | Result(%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (104/104)*100 = 100%
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/104)*100 = 0%
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Written) * 100 | (93/104)*100 = 90.4%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Written) * 100 | (10/104)*100 = 9.6%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Written) * 100 | (0/104)*100 = 0%
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A